Evaluation Report Title: / Trade in Global Value Chains Initiative Mid-Term Evaluation Report

Response to Evaluation Report (overarching narrative)
The Trade in Global Value Chains Initiative is a DFID-funded programme to support improved employment opportunities and working conditions and build more resilient supply chains within the horticulture sector in Kenya and South Africa and the garments sector in Bangladesh. DFID is working with private sector and NGO partners to achieve this, through 20 projects supporting workers in a number of different ways, including skills, health, management and engagement with smallholders, with matched funding from DFID and private sector partners. / The programme began in 2013 and all project activities will finish by December 2016. This report is a mid-term evaluation, representing a review of the evidence so far (up to October 2015), providing formative recommendations for the programme and recommendations for future programming decisions. / We would like to thank the Evaluation Management Unit for producing this report, and the substantial amount of work that has gone into it. It is still too early to judge the overall effectiveness of TGVCI, but this Mid Term Report provides a useful view of progress so far. / TGVCI has had a number of successes and positive results. There is some evidence that projects building the skills of permanent, season workers and unemployed people have provided immediate benefits, such as improved self-confidence, self-esteem and understanding of work responsibilities. Projects working on worker health and nutrition have shown benefits in the quality of employment and work conditions. Projects focussed on management and worker dialogue have shown initial benefits in reduced absenteeism, reduced labour turnover and improved worker satisfaction. Despite the monitoring and evaluation challenges, the overall value for money picture of TGVCI is a positive one. The TGVCI contract value is £4.6m of which the management fee element is 13.6%. TGVCI has been able to attract 43 companies covering 20 projects. These private companies have contributed approximately £2m. TGVCI has benefited 102,000 people directly (1.1 million indirectly), working in farms and factories in Kenya, South Africa and Bangladesh with improved working conditions, health and training opportunities. This includes 34,437 women directly (and 490,839 indirectly). / We recognise that there have been substantial challenges in data collection for this evaluation and showing strong causal evidence of impacts will be difficult. The theory-based approach of the evaluation will seek to test the theory of change in the different impact pathways tested by the TGVCI projects. Using some projects as case studies will help provide more detailed data in some areas, but the quality of evidence will vary across the projects and it may prove difficult to provide general conclusions. / However, the formative evaluation provided of the programme design and sustainability is helpful to DFID broader work promoting economic development and working with the private sector to deliver improved outcomes for workers and businesses in our focus countries. DFID has in particular learned lessons regarding understanding of commercial sensitivity. / This Mid Term Evaluation Report provides recommendations in two categories. First there are the recommendations for the current programme – we respond to these in turn below. The Report also provides 11 recommendations for a potential follow-on programme or second phase of TGVCI. As these recommendations refer to hypothetical future programming, we cannot accept or reject these at this point. However, these recommendations have been taken on board and will be considered when DFID takes future decisions on programme in trade and global value chains.

Evaluation Report Title: Trade in Global Value Chains Initiative Mid Term Evaluation Report

Recommendations	Accepted or Rejected	If “Accepted”, Action plan for Implementation or if “Rejected”, Reason for Rejection
The Project Management Unit (PMU) should consult with projects with respect to timing and resources, to establish where more time is needed for completion and look favourably upon requests for justified changes to plans and funding, given the short duration allowed for the projects by the fund design.	Accepted	Since the Mid-Term Evaluation Report was written, the TGVCI programme has been granted a time extension, from September 2016 to December 2016. This extension is specifically to allow some Round 2 projects time to complete their activities.
Resources allowing, PMU should draw up a learning strategy for in-country project interaction and lesson learning, and support projects’ early dissemination/communication planning.	Partially accepted	We agree with the importance of facilitating lesson learning between projects within TGVCI. DFID is promoting lesson-learning through seminars and workshops hosted by DFID and PMU. The Evaluation Management Unit will also be holding learning events in each country in 2017 which will share lessons and discuss the findings of the evaluation. When starting Round 2, PMU arranged for exiting grantees to share lessons with new applicants. Given the existing processes in place and the scope for further convening by DFID, we have decided not to allocate extra resources for PMU to produce a learning strategy. However, DFID will plan for additional learning activities in the final stages of the programme and after project completion, within current resources.
The Evaluation Management Unit (EMU) should continue to generate evidence on outcomes and impacts, including case studies on round 2 projects, and engage with stakeholders in workshops in 2016 to explore preliminary findings on the programme theory of change, including at the sector level.	Accepted	DFID agrees that EMU should continue with its work to generate evidence and engage with project partners and stakeholders.